## Avsec Mandays
| Tasks | Mandays | Additional Information
Backend | Creating 2 roles | 1 | Local Kuk & HQ Kuk
| Creating 3 Terminals | 2
| CALMS Integration | 5 | Requirements, Go through Documentation, Discussion, Doubts Clarification
| Alter table for CALMS Integration | 5
| RabbitMQ Listener for CALMS | 5
| New Permanent Pass Application Flow | 5
| Renewal Permanent Pass Application Flow | 5
| Change Permanent Pass Application Flow | 5
| Email/ Notification Triggering | 5
| Upload Download Documents | 2
| 1 Complex Reports (Incase structure changes or New Report format) | 2 | 1 complex reports will take 2 days
2 simple reports will take 1 day
Testing | Avsec Admin adds Company Admin | 1
Company Admin adds Company Internal Admin
Company Admin creates New Pass
Company Admin creates Renew Pass
Company Admin creates Change Pass
| Positive Flow Test for New Pass, Renew Pass & Change Pass | 3 | Create Pass -> Review Pass {Local Kuk & Hq Kuk} -> Approve Pass
| Negative Flow Test for New Pass, Renew Pass & Change Pass | 3 | Rollback the flow
| 3 Complex Reports | 2 | Testing reports includes checking the values & Security Testing
5 simple reports will take 1 day
3 complex reports will take 2 days
| Security Testing for the UI Level | 2
| Security Testing for the API Level | 2
| Test Existing System | 1 | To ensure the existing system not getting impacted due to the changes
56